## Sheet1
Priority # | Asset # | FINAL Asset name | CHANGE ASSET NAME TO. . . . . | Name from TCS | Already created in VR Course | Category | Asset type | Subcategory | Associated with | Level of need (10 must have, 1 nice to have) | Requires customization | Complexity | Description | Requirements (interactivity) | Details (url) | Status | Comments/Feedback | Approved by SCE? | Potential course/ program | Deadline | Contact
| 1 | SCE_Misc_House1 |  | House_1_OH_No Esr | Meter Spotting | Misc | [9 empty] | Published in SCE Group | Can you make front door set to open to 90 degrees, and to close?
| 2 | SCE_Misc_House2 |  | House_2_OH_Esr | Meter Spotting | Misc | [9 empty] | Published in SCE Group
| 3 | SCE_Misc_House3 |  | House_3_OH_Esr | Meter Spotting | Misc | [9 empty] | Published in SCE Group | The roofline and above the doors are very flickering. Also when we move closer to front door the resolution of the stone goes from blurry to clear. Possible to fix? Possible to have door swing open/close?
| 4 | SCE_Misc_Chair_Patio |  | House_3_Patio chair | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 5 | SCE_Misc_Table_Patio |  | House_3_Patio table | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 6 | SCE_Misc_House4 |  | House_4_UG_Esr | Meter Spotting | Misc | [9 empty] | Published in SCE Group | This house looks very low resolution. Would take too much time to redo, so skip it
| 7 | SCE_Misc_House5 |  | House_5_OH_Esr | Meter Spotting | Misc | [9 empty] | Published in SCE Group | The front door and shutters to the left of front door are very flickering. Looks like there are holes everywhere and the shutters are falling apart. Can you update?
| 8 | SCE_Misc_House6 |  | House_6 | Meter Spotting | Misc | [9 empty] | Published in SCE Group | Can you add a door handle to front door. And, can you make front door set to open to 90 degrees, and to close?
| 9 | SCE_Misc_Fence_Wood |  | Wooden Fencing | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 10 | SCE_Misc_Gate_Wood_ANIM | Misc_Gate_Wood_ANIM | Wooden Gate | Meter Spotting | Misc | [7 empty] | ANIMATION- would like ability to have left side fence gate panel open to 90 degree angle |  | Published in SCE Group
| 11 | SCE_Misc_Road1 | (Dirt? Asphalt? Add at end… Misc_Road_Asphalt2Ln) | Road | Meter Spotting | Misc | [9 empty] | Published in SCE Group | Would be great if it was "solid", with a collider so one could actually be on it.
| 12 | SCE_Misc_Footpath |  | Footpath | Meter Spotting | Misc | [9 empty] | Published in SCE Group | Would be great if it was "solid", with a collider so one could actually be on it. Also when you move towards it, the light resolution seems to sweep over it, making part of path blurry, part clear.
| 13 | SCE_Misc_Ground_Green | (Grass? Add grass if so… Misc_Ground_Grass) | Green ground | Meter Spotting | Misc | [9 empty] | Published in SCE Group | Would be great if it was "solid", with a collider so one could actually be on it.
| 14 | SCE_Misc_Fence_Green | Misc_Fence_ (Wood/Wire)_Green | Green fence | Meter Spotting | Misc | [9 empty] | Published in SCE Group | Shape looks like a balloon couch. It's very shiny and not realistic like a hedge. Can you make it not as smooth looking with greater resolution texture? Would be great if it was "solid", with colliders so one couldn't go through it but had to go around or jump on top of it (?) or over it (?)
| 15 | SCE_OH_Pole1 |  | Electric wood pole | Meter Spotting | OH | Pole | [8 empty] | Published in SCE Group |  | Y
| 16 | SCE_OH_Pole_Material_CrossArm |  | Cross arm | Meter Spotting | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 17 | SCE_OH_Pole_Material_PinInsulator1 |  | Pin insulator | Meter Spotting | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 17.1 | SCE_OH_Material_Weatherhead |  | Weatherhead | Meter Spotting | [7 empty] | This wasn't on asset list but was created in Meter Spotting VR course. Can you includethis asset please |  |  | Published in SCE Group |  | Y
| 18 | SCE_OH_Pole_Wire1 |  | Electric pole wire | Meter Spotting | OH | wire |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 19 | SCE_Misc_TrashCan_blue |  | Trash Bin_blue | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 20 | SCE_Misc_TrashCan_black |  | Trash Bin_black | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 21 | SCE_OH_MeterBox_frame | st list | Meter Box_base frame | Meter Spotting | OH | equipment |  | Meter |  |  |  |  | would like full meter box (no measuring equipment) as one item |  | Published in SCE Group |  | Y
| 21.1 | SCE_OH_MeterBox_Full | [13 empty] | Published in SCE Group | Please review animation videos sent via email by Engage and see if you can set the States so animation doesn't loop
| 22 | SCE_OH_MeterBox_meter |  | Meter Box_round meter | Meter Spotting | OH | equipment |  | Meter |  |  |  |  | also would like each component of meter box as separate items |  | Published in SCE Group |  | Y
| 23 | SCE_OH_MeterBox_WiringPanel_ANIM | OH_MeterBox_WiringPanel_ANIM | Meter Box_wiring panel | Meter Spotting | OH | equipment |  | Meter |  |  |  |  | ANIMATION- Meter Box_panel left to be able to rotate/tile upwardsfrom top of frame to 90 degree angle |  | Published in SCE Group | Please review animation videos sent via email by Engage and see if you can set the States so we can control the animation
| 24 | SCE_OH_MeterBox_panel_right |  | Meter Box_panel right | Meter Spotting | OH | equipment |  | Meter | [6 empty] | Published in SCE Group |  | Y
| 25 | SCE_OH_MeterBox_right_panel_fuse |  | Meter Box_right panel fuse | Meter Spotting | OH | equipment |  | Meter | [6 empty] | Published in SCE Group | Need to use higher resolution image. It's very blurry
| 26 | SCE_OH_MeterBox_wire_left | OH_MeterBox_wire_left (removed space) | Meter Box_wire left | Meter Spotting | OH | equipment |  | Meter | [6 empty] | Published in SCE Group |  | Y
| 27 | SCE_OH_MeterBox_wire_middle | OH_MeterBox_wire_middle (removed space) | Meter Box_wire middle | Meter Spotting | OH | equipment |  | Meter | [6 empty] | Published in SCE Group |  | Y
| 28 | SCE_OH_MeterBox_wire_right | OH_MeterBox_wire_right (removed space) | Meter Box_wire right | Meter Spotting | OH | equipment |  | Meter | [6 empty] | Published in SCE Group |  | Y
| 29 | SCE_OH_MeterBox_MeasureEquipment |  | Meter Box_measuring equipment | Meter Spotting | OH | equipment |  | Meter | [6 empty] | Published in SCE Group |  | Y
| 30 | SCE_OH_MeterConduit1 |  | Overhead meter pipe | Meter Spotting | OH | Material |  | Meter | [6 empty] | Published in SCE Group |  | Y
| 31 | SCE_OH_MeterConduit2 | UG_MeterConduit | Underground meter pipe | Meter Spotting | OH | material |  | Meter | [6 empty] | Published in SCE Group |  | Y
| 32 | SCE_OH_MeterPipeClamp |  | Meter pipe clamp | Meter Spotting | OH | material |  | Meter | [6 empty] | Published in SCE Group |  | Y
| 33 | SCE_Misc_Bicycle |  | Bicycle | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 34 | SCE_Misc_GasMeter |  | Gas meter | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 35 | SCE_Misc_GardenHose_faucet |  | Garden hose_faucet | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 36 | SCE_Misc_Pitchfork |  | Gardening tool_Pitchfork | Meter Spotting | Misc | [9 empty] | Published in SCE Group | The trigger selection should be in middle of handle, not at very top of item
| 37 | SCE_Misc_Rake |  | Gardening tool_Rake | Meter Spotting | Misc | [9 empty] | Published in SCE Group | The trigger selection should be in middle of handle, not at very top of item
| 38 | SCE_Misc_Broom |  | Gardening tool_Broom | Meter Spotting | Misc | [9 empty] | Published in SCE Group | The trigger selection should be in middle of handle, not at very top of item
| 39 | SCE_Misc_Shovel |  | Gardening tool_Shovel | Meter Spotting | Misc | [9 empty] | Published in SCE Group | The trigger selection should be in middle of handle, not at very top of item
| 40 | SCE_Misc_WoodPile |  | Wood pile | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 41 | SCE_Misc_DogHouse | Misc_DogHouse | Dog house | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 42 | SCE_Misc_DogBone | Misc_DogBone | Dog bone | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 43 | SCE_Misc_ACUnit |  | AC unit | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 44 | SCE_Misc_Car1 |  | Car | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 45 | SCE_Misc_DogBowl | Misc_DogBowl | Dog bowl | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 46 | SCE_Misc_DogSign | Misc_DogSign | Dog sign | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 47 | SCE_Misc_GarbageBag |  | Garbage bag | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 48 | SCE_Tool_TrafficCone1 |  | Cone | Meter Spotting | Tool | [9 empty] | Published in SCE Group |  | Y
| 49 | SCE_OH_Material_MeterSticker |  | Yellow Sticker | Meter Spotting | OH | [9 empty] | Published in SCE Group | can sticker be more legible? Higher definition image?
| 50 | SCE_Misc_CellRelayMeter |  | Cell relay meter | Meter Spotting | Misc | [9 empty] | Published in SCE Group |  | Y
| 51 | SCE_Misc_TreePot |  | Tree pot | Meter Spotting | Misc
| 52 | SCE_Misc_Tree1 |  | Tree_1 | Meter Spotting | Misc
| 53 | SCE_Misc_Tree2 |  | Tree_2 | Meter Spotting | Misc
| 54 | SCE_Misc_Tree3 |  | Tree_3 | Meter Spotting | Misc
| 55 | SCE_Misc_Bushes1 |  | Bushes_1 | Meter Spotting | Misc
| 56 | SCE_Misc_Bushes2 |  | Bushes_2 | Meter Spotting | Misc
| 57 | SCE_Misc_Bushes3 |  | Bushes_3 | Meter Spotting | Misc
| 58 | SCE_OH_pole_WoodPole40 |  | Wood secondary pole 40' | OH | OH | pole | [8 empty] | Published in SCE Group |  | Y
| 59 | SCE_OH_pole_wire_Triplex1 |  | Wood secondary pole 40'_Triplex wire | OH | OH | wire |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 60 | SCE_OH_pole_Streetlight |  | Street light | OH | OH | equipment |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 61 | SCE_OH_pole_Streetlight_wires |  | Street light connecting wires | OH | OH | equipment |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 62 | SCE_OH_pole_material_Unistrut |  | Unistrut | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 63 | SCE_OH_pole_material_Unistrut_bolt |  | Unistrut_bolt | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 64 | SCE_OH_pole_material_Riser |  | Riser | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 65 | SCE_OH_pole_material_riser_clamp |  | Riser_clamp | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 66 | SCE_OH_pole_wire_TelecomWire |  | Wood secondary pole 40'_Telecome Wire | OH | OH | wire |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 67 | SCE_OH_pole_wire_CommWire1 |  | Wood secondary pole 40'_Communication wire | OH | OH | wire |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 68 | SCE_OH_pole_material_GuyWire2 |  | Wood secondary pole 40'_Span guy wire | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 69 | SCE_OH_pole_material_HyPlug |  | Wood secondary pole 40'_HyPlug | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 70 | SCE_OH_pole_wire_TelecomBox |  | Telecome device | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 71 | SCE_OH_pole_material_OneBolt |  | One bolt | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 72 | SCE_OH_pole_material_BoltInsulator3inch |  | 3” bolt insulator | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 73 | SCE_OH_pole_material_GuyWire_Attachment |  | Guy wire attachment | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 74 | SCE_OH_pole_material_GuyWire1 |  | Down guy wire | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group | I didn't know the three wires were all one asset. Can you split them into three different guy wires so we can put them at different angles on poles? and can you see the image to right? Coming from the yellow is just a loop of metal wire. Your model looks like a bracket. Can you update?
| 75 | SCE_OH_pole_material_GuyWire_Anchor |  | Down guy_Anchor | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 76 | SCE_OH_pole_WoodPole45 |  | Wood pole 45' | OH | OH | pole | [8 empty] | Published in SCE Group |  | Y
| 77 | SCE_OH_pole_material_PrimaryArm3 |  | Wood pole 45'_primary arm | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 78 | SCE_OH_pole_material_BuckArm1 |  | Wood pole 45'_buck arm | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 79 | SCE_OH_pole_wire_Triplex2 |  | Wood pole 45'_secondary wire_triplex | OH | OH | wire |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 80 | SCE_OH_pole_equipment_Transformer |  | Single transformer | OH | OH | equipment |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 81 | SCE_OH_pole_wire_CommWire2 |  | Wood pole 45'_communication wire | OH | OH | wire |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 82 | SCE_OH_pole_wire_CommWire3 |  | Wood pole 45'_telephone wire | OH | OH | wire |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 83 | SCE_OH_pole_material_AvianShield |  | Avian shield | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 84 | SCE_OH_pole_wire_PrimaryWire1 |  | Wood pole 45'_primary wire | OH | OH | wire |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 85 | SCE_OH_pole_wire_PrimaryWire2 |  | Wood pole 45'_buck arm wire | OH | OH | wire |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 86 | SCE_OH_pole_CompositePole50 |  | Composite pole 50' | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 87 | SCE_OH_pole_material_PrimaryArm1 |  | Composite pole 50'_Primary arm | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 88 | SCE_OH_pole_material_FuseArm2 |  | Composite pole 50'_fuse arm | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 89 | SCE_OH_pole_equipment_3PTransformer |  | Three phase transformer | OH | OH | [9 empty] | Published in SCE Group |  | Y
| 90 | SCE_OH_pole_material_Fuse1 |  | Fuse | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 91 | SCE_OH_pole_WoodPole50_FireWrap |  | Fire wrapped wood pole 50' | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 92 | SCE_OH_pole_LWSPole85 |  | Light weight steel 60' | OH | OH | pole | [8 empty] | Published in SCE Group |  | Y
| 93 | SCE_OH_pole_material_DoubleArm1 |  | Steel_10' double arm | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 94 | SCE_OH_pole_material_ArmComposite2 |  | Steel_12' composite single arm | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 95 | SCE_OH_pole_material_FuseArm3 |  | Steel_fuse arm | OH | OH | material |  | Pole | [6 empty] | Published in SCE Group |  | Y
| 96 | SCE_OH_pole_material_PriArm_DbleDeadEnd |  | Fire wrapped wood pole 50'_double dead end primary arm | OH | OH | pole
| 97 | SCE_OH_pole_Base |  | Pole base | OH | OH | material |  | Pole
| 98 | SCE_OH_pole_material_yellowstripe |  | Wood poles_yellow strip | OH | OH | material |  | Pole
| 99 | SCE_OH_pole_material_PrimaryArm2 |  | Single primary arm | OH | OH | material |  | Pole
| 100 | SCE_OH_pole_material_BuckArm2 |  | Buck arm primary | OH | OH | material |  | Pole
| 101 | SCE_OH_pole_material_DbleArmComp |  | Composite double arm | OH | OH | material |  | Pole
| 102 | SCE_OH_pole_material_ArmComp1 |  | Composite single arm | OH | OH | material |  | Pole
| 103 | SCE_OH_pole_material_PinInsulator2 |  | Pin insulator | OH | OH | material |  | Pole
| 104 | SCE_OH_pole_material_FuseArm4 |  | Fuse arm | OH | OH | material |  | Pole
| 105 | SCE_Misc_Sign1 |  | Pole number_1 | OH | Misc
| 106 | SCE_Misc_Sign2 |  | Pole number_2 | OH | Misc
| 107 | SCE_Misc_Sign3 |  | Pole number_3 | OH | Misc
| 108 | SCE_Misc_Sign4 |  | Pole number_4 | OH | Misc
| 109 | SCE_Misc_Sign5 |  | Pole number_5 | OH | Misc
| 110 | SCE_Misc_Sign6 |  | Pole number_6 | OH | Misc
| 111 | SCE_OH_pole_material_DeadEndInsulator |  | Dead end insulator | OH | OH | material |  | Pole
| 112 | SCE_OH_pole_material_3SpoolRack |  | 3 spool rack | OH | OH | material |  | Pole
| 113 | SCE_OH_pole_wire_ConnectingWire1 |  | Composite pole 50'_fuse to transformer connecting wire_1 | OH | OH | material |  | Pole
| 114 | SCE_OH_pole_wire_ConnectingWire2 |  | Composite pole 50'_pin insulator to fuse connecting wire | OH | OH | material |  | Pole
| 115 | SCE_OH_pole_wire_ConnectingWire3 |  | Composite pole 50'_fuse to transformer connecting wire_2 | OH | OH | material |  | Pole
| 116 | SCE_OH_pole_wire_ConnectingWire4 |  | Composite pole 50'_fuse to transformer connecting wire_3 | OH | OH | material |  | Pole
| 117 | SCE_OH_pole_wire_ConnectingWire5 |  | Composite pole 50'_transformer to triplex connecting wire_1 | OH | OH | material |  | Pole
| 118 | SCE_OH_pole_wire_ConnectingWire6 |  | Composite pole 50'_transformer to triplex connecting wire_2 | OH | OH | material |  | Pole
| 119 | SCE_OH_pole_wire_ConnectingWire7 |  | Composite pole 50'_transformer to triplex connecting wire_3
| 120 | SCE_OH_pole_wire_ConnectingWire8 |  | Fire wood pole 50 Pin insulator wire 1 | OH | OH | material |  | Pole
| 121 | SCE_OH_pole_wire_ConnectingWire11 |  | Fire wood pole 50 Pin insulator wire 2 | OH | OH | material |  | Pole
| 122 | SCE_OH_pole_wire_PrimaryWire3 |  | Fire wood pole 50 Primary wire 1 | OH | OH | wire |  | Pole
| 123 | SCE_OH_pole_wire_PrimaryWire4 |  | Fire wood pole 50 Primary wire 2 | OH | OH | wire |  | Pole
| 124 | SCE_OH_pole_material_GuyWire3 |  | Fire wood pole 50 down guy wire | OH | OH | material |  | Pole
| 125 | SCE_OH_pole_material_GuyAnchor4 |  | Fire wood pole 50 down guy anchor | OH | OH | material |  | Pole
| 126 | SCE_OH_pole_wire_ConnectingWire7 |  | Light weight steel 60 double ded end insulator connecting wire | OH | OH | material |  | Pole
| 127 | SCE_OH_pole_wire_PrimaryWire5 |  | Light weight steel 60 Primary wire 1 | OH | OH | material |  | Pole
| 128 | SCE_OH_pole_wire_PrimaryWire6 |  | Light weight steel 60 Primary wire 2 | OH | OH | material |  | Pole
| 129 | SCE_OH_pole_wire_cable1 |  | Light weight steel 60 Steel_12' composite single arm cable | OH | OH | material |  | Pole
| 130 | SCE_OH_pole_wire_ConnectingWire9 |  | Light weight steel 60 pin insulator to fuse arm cable 1 | OH | OH | material |  | Pole
| 131 | SCE_OH_pole_wire_ConnectingWire10 |  | Light weight steel 60 pin insulator to fuse arm cable 2 | OH | OH | material |  | Pole
| 132 | SCE_OH_pole_wire_ConnectingWire12 |  | Light weight steel 60 fuse arm to transformer cable 1 | OH | OH | material |  | Pole
| 133 | SCE_OH_pole_wire_ConnectingWire13 |  | Light weight steel 60 fuse arm to transformer cable 2 | OH | OH | material |  | Pole
| 134 | SCE_OH_pole_wire_cable2 |  | Light weight steel 60 communication cable | OH | OH | material |  | Pole
| 135 | SCE_OH_pole_wire_ConnectingWire14 |  | Light weight steel 60 transformer to communication cable wire 1 | OH | OH | material |  | Pole
| 136 | SCE_OH_pole_wire_ConnectingWire15 |  | Light weight steel 60 transformer to communication cable wire 2 | OH | OH | material |  | Pole
| 137 | SCE_OH_pole_wire_ConnectingWire16 |  | Wood pole 45'_transformer to secondary wire_2 | OH | OH | material |  | Pole
| 138 | SCE_Misc_Wall |  | Boundry wall | OH | OH
| 139 | SCE_Misc_Ground |  | Ground | OH | OH
| 140 | SCE_UG_Pullbox_Base |  | Pullbox_Base | UG | UG | material |  | Pullbox
| 141 | SCE_UG_Pullbox_Lid_left |  | Pullbox Lid_left | UG | UG | material |  | Pullbox
| 142 | SCE_UG_Pullbox_Lid_right |  | Pullbox Lid_right | UG | UG | material |  | Pullbox
| 143 | SCE_UG_Pullbox_Frame |  | Pullbox frame | UG | UG | material |  | Pullbox
| 144 | SCE_UG_Material_JbarA |  | Pullbox_Jbar A | UG | UG | material
| 145 | SCE_UG_Material_JbarB |  | Pullbox_Jbar B | UG | UG | material
| 146 | SCE_UG_Material_JbarC |  | Pullbox_Jbar C | UG | UG | material
| 147 | SCE_UG_Material_JbarA_Wire1 |  | Pullbox_Jbar A_Wire 1 | UG | UG | material
| 148 | SCE_UG_Material_JbarA_Wire2 |  | Pullbox_Jbar A_Wire 2 | UG | UG | material
| 149 | SCE_UG_Material_JbarA_Wire3 |  | Pullbox_Jbar A_Wire 3 | UG | UG | material
| 150 | SCE_UG_Material_JbarB_Wire1 |  | Pullbox_Jbar B_Wire 1 | UG | UG | material
| 151 | SCE_UG_Material_JbarB_Wire2 |  | Pullbox_Jbar B_Wire 2 | UG | UG | material
| 152 | SCE_UG_Material_JbarB_Wire3 |  | Pullbox_Jbar B_Wire 3 | UG | UG | material
| 153 | SCE_UG_Material_JbarC_Wire1 |  | Pullbox_Jbar C_Wire 1 | UG | UG | material
| 154 | SCE_UG_Material_JbarC_Wire2 |  | Pullbox_Jbar C_Wire 2 | UG | UG | material
| 155 | SCE_UG_Material_JbarC_Wire3 |  | Pullbox_Jbar C_Wire 3 | UG | UG | material
| 156 | SCE_UG_Vault_Base |  | Vault_Base | UG | UG | material |  | Vault
| 157 | SCE_UG_Vault_frame |  | Vault_frame | UG | UG | material |  | Vault
| 158 | SCE_UG_Vault_squareLid |  | Vault_square lid | UG | UG | material |  | Vault
| 159 | SCE_UG_Vault_roundLid |  | Vault_round lid | UG | UG | material |  | Vault
| 160 | SCE_UG_Vault_stairs |  | Vault_stairs | UG | UG | material |  | Vault
| 161 | SCE_UG_Vault_Jbar |  | Vault_Jbar | UG | UG | material
| 162 | SCE_UG_Vault_Equipment_Switch |  | Vault_Switch box | UG | UG | equipment |  | Vault
| 163 | SCE_UG_Equipment_Transformer1 |  | Vault_transformer | UG | UG | equipment
| 164 | SCE_UG_Burd_Base |  | Burd_Base | UG | UG | material |  | BURD
| 165 | SCE_UG_Burd_Mesh |  | Burd_Mesh | UG | UG | material |  | BURD
| 166 | SCE_UG_Burd_Lid |  | Burd_Lid | UG | UG | material |  | BURD
| 167 | SCE_UG_Burd_Transformer |  | Burd_Transformer | UG | UG | equipment |  | BURD
| 168 | SCE_UG_SlabBox1 |  | Slab box1 | UG | UG | material |  | Slab Box
| 169 | SCE_UG_Slab box_Transformer_leftdoor_ANIM |  | Slab box Transformer left door | UG | UG | material | Transformer | Slab Box |  |  |  |  | ANIMATION- would like ability to have left side transformer door open to 120 degree angle outwards
| 170 | SCE_UG_SlabBox_Transformer_rightdoor_ANIM |  | Slab box Transformer right door | UG | UG | material | Transformer | Slab Box |  |  |  |  | ANIMATION- would like ability to have right side transformer door open to 120 degree angle outwards
| 171 | SCE_UG_SlabBox_Transformer1 |  | Slab box Transformer1 | UG | UG | equipment | Transformer | Slab Box
| 172 | SCE_UG_SlabBox_Transformer_Exterior |  | Slab box Transformer Exterior | UG | UG | material | Transformer | Slab Box
| 173 | SCE_UG_SlabBox_Transformer_cableH1 |  | Slab box Transformer cable H1 | UG | UG | material | Transformer | Slab Box
| 174 | SCE_UG_SlabBox_Transformer_cableH2 |  | Slab box Transformer cable H2 | UG | UG | material | Transformer | Slab Box
| 175 | SCE_UG_SlabBox_Transformer_cableH3 |  | Slab box Transformer cable H3 | UG | UG | material | Transformer | Slab Box
| 176 | SCE_UG_SlabBox_Transformer_cableX0Blue |  | Slab box Transformer cable X0 blue | UG | UG | material | Transformer | Slab Box
| 177 | SCE_UG_SlabBox_Transformer_cableX0Black |  | Slab box Transformer cable X0 black | UG | UG | material | Transformer | Slab Box
| 178 | SCE_UG_SlabBox_Transformer_cableX1 |  | Slab box Transformer cable X1 | UG | UG | material | Transformer | Slab Box
| 179 | SCE_UG_SlabBox_Transformer_cableX2 |  | Slab box Transformer cable X2 | UG | UG | material | Transformer | Slab Box
| 180 | SCE_UG_SlabBox_Transformer_Xconnect |  | Slab box Transformer X Connector | UG | UG | material | Transformer | Slab Box
| 181 | SCE_UG_SlabBox_Transformer_Hconnect |  | Slab box Transformer H Connector | UG | UG | material | Transformer | Slab Box
| 182 | SCE_UG_Slab box_Transformer_HSwitch |  | Slab box Transformer H Switch | UG | UG | material | Transformer | Slab Box
| 183 | SCE_UG_Slab box_Transformer_HSwitchCover |  | Slab box Transformer H Switch Cover | UG | UG | material | Transformer | Slab Box
| 184 | SCE_UG_Material_FuelGauge |  | Fuel gauge | UG | UG | material | Transformer | Slab Box
| 185 | SCE_UG_Materials_CoilSwitch |  | Coil SW | UG | UG | material | Transformer | Slab Box
| 186 | SCE_UG_PME_Exterior_box |  | PME Exterior box | UG | UG | equipment |  | PME
| 187 | SCE_UG_PME_ConcreteBase |  | PME Concreate box | UG | UG | material |  | PME
| 188 | SCE_UG_PadmountTransformer1P |  | Single phase padmounted transformer | UG | UG | equipment | Transformer
| 189 | SCE_UG_Material_Elbow |  | Elbow | UG | UG | material
| 190 | SCE_UG_Material_Jbars |  | J bars | UG | UG | material
| 191 | SCE_UG_Equipment_Transformer2 |  | Transformer | UG | UG | equipment | Transformer
| 192 | SCE_UG_Equipment_Transformer_Cable1 |  | Transformer vault cable 1 | UG | UG | material | Transformer
| 193 | SCE_UG_Equipment_Transformer_Cable2 |  | Transformer vault cable 2 | UG | UG | material | Transformer
| 194 | SCE_UG_Equipment_Transformer_Cable3 |  | Transformer vault cable 3 | UG | UG | material | Transformer
| 195 | SCE_UG_Equipment_Transformer_Cable4 |  | Transformer vault cable 4 | UG | UG | material | Transformer
| 196 | SCE_UG_Equipment_SwitchtoJbar_Wire1 |  | Switch Box to Jbar wire 1 | UG | UG | material | Transformer
| 197 | SCE_UG_Equipment_SwitchtoJbar_Wire2 |  | Switch Box to Jbar wire 2 | UG | UG | material | Transformer
| 198 | SCE_UG_Equipment_SwitchtoJbar_Wire3 |  | Switch Box to Jbar wire 3 | UG | UG | material | Transformer
| 199 | SCE_UG_Equipment_SwitchtoJbar_Wire4 |  | Switch Box to Jbar wire 4 | UG | UG | material | Transformer
| 200 | SCE_UG_Equipment_SwitchtoJbar_Wire5 |  | Switch Box to Jbar wire 5 | UG | UG | material | Transformer
| 201 | SCE_UG_Equipment_SwitchtoJbar_Wire6 |  | Switch Box to Jbar wire 6 | UG | UG | material | Transformer
| 202 | SCE_UG_Equipment_SwitchtoJVault_Cable1 | Should J be removed from name? haven't heard of jvault… could be my lack of knowledge? | Switch Box to vault cable 1 | UG | UG | material | Transformer
| 203 | SCE_UG_Equipment_SwitchtoJVault_Cable2 |  | Switch Box to vault cable 2 | UG | UG | material | Transformer
| 204 | SCE_UG_Equipment_SwitchtoJVault_Cable3 |  | Switch Box to vault cable 3 | UG | UG | material | Transformer
| 205 | SCE_UG_Equipment_JBartoJVault_Cable1 |  | JBar to vault cable 1 | UG | UG | material | Transformer
| 206 | SCE_UG_Equipment_JBartoJVault_Cable2 |  | JBar to vault cable 2 | UG | UG | material | Transformer
| 207 | SCE_UG_Equipment_JBartoJVault_Cable3 |  | JBar to vault cable 3 | UG | UG | material | Transformer
| 208 | SCE_UG_BurdTransformer_Cable1 |  | Burd Transformer to Utilco bar cable 1 | UG | UG | material | Transformer
| 209 | SCE_UG_BurdTransformer_Cable2 |  | Burd Transformer to Utilco bar cable 2 | UG | UG | material | Transformer
| 210 | SCE_UG_BurdTransformer_Cable3 |  | Burd Transformer to Utilco bar cable 3 | UG | UG | material | Transformer
| 211 | SCE_UG_BurdTransformer_Cable4 |  | Burd Transformer to Utilco bar cable 4 | UG | UG | material | Transformer
| 212 | SCE_UG_Burd_Wire1 |  | Burd Utilco bar to Burd Connecting wire 1 | UG | UG | material | Transformer
| 213 | SCE_UG_Burd_Wire2 |  | Burd Utilco bar to Burd Connecting wire 2 | UG | UG | material | Transformer
| 214 | SCE_UG_Burd_Wire3 |  | Burd Utilco bar to Burd Connecting wire 3 | UG | UG | material | Transformer
| 215 | SCE_UG_Burd_Wire4 |  | Burd Utilco bar to Burd Connecting wire 4 | UG | UG | material | Transformer
| 216 | SCE_UG_Burd_Wire5 |  | Burd Utilco bar to Burd Connecting wire 5 | UG | UG | material | Transformer
| 217 | SCE_UG_Burd_Wire6 |  | Burd Utilco bar to Burd Connecting wire 6 | UG | UG | material | Transformer
| 218 | SCE_UG_SlabBox2 |  | Slab box2 | UG | UG | material |  | Slab Box
| 219 | SCE_UG_Transformer_CopperWire1 |  | 3P Transformer Copper wire assembly | UG | UG | material | Transformer
| 220 | SCE_UG_Transformer_CopperWire2 |  | Copper wire connector | UG | UG | material | Transformer
| 221 | SCE_UG_Transformer_CopperWire3 |  | Copper wire type 1 | UG | UG | material | Transformer
| 222 | SCE_UG_Transformer_CopperWire4 |  | Copper wire type 2 | UG | UG | material | Transformer
| 223 | SCE_UG_Transformer_CopperWire5 |  | Copper wire type 3 | UG | UG | material | Transformer
| 224 | SCE_UG_Transformer_CopperWire6 |  | Copper wire main | UG | UG | material | Transformer
| 225 | SCE_UG_SlabBox_Transformer2 |  | Slab box transformer 2 | UG | UG | equipment | Transformer | Slab Box
| 226 | SCE_UG_SlabBox_Transformer2_ H1A cable |  | Slab box transformer 2 H1A cable | UG | UG | material | Transformer
| 227 | SCE_UG_SlabBox_Transformer2_ H2A cable |  | Slab box transformer 2 H2A cable | UG | UG | material | Transformer
| 228 | SCE_UG_SlabBox_Transformer2_ H3A cable |  | Slab box transformer 2 H3A cable | UG | UG | material | Transformer
| 229 | SCE_UG_SlabBox_Transformer2_ H1B cable |  | Slab box transformer 2 H1B cable | UG | UG | material | Transformer
| 230 | SCE_UG_SlabBox_Transformer2_ H2B cable |  | Slab box transformer 2 H2B cable | UG | UG | material | Transformer
| 231 | SCE_UG_SlabBox_Transformer2_ H3B cable |  | Slab box transformer 2 H3B cable | UG | UG | material | Transformer
| 232 | SCE_UG_Material_CopperWire_H1A |  | Copper wire H1A | UG | UG | material | Transformer
| 233 | SCE_UG_Material_CopperWire_H2A |  | Copper wire H2A | UG | UG | material | Transformer
| 234 | SCE_UG_Material_CopperWire_H3A |  | Copper wire H3A | UG | UG | material | Transformer
| 235 | SCE_UG_Material_CopperWire_H1B |  | Copper wire H1B | UG | UG | material | Transformer
| 236 | SCE_UG_Material_CopperWire_H2B |  | Copper wire H2B | UG | UG | material | Transformer
| 237 | SCE_UG_Material_CopperWire_H3B |  | Copper wire H3B | UG | UG | material | Transformer
| 238 | SCE_UG_Material_CopperWireBase |  | Copper wire base | UG | UG | material | Transformer
| 239 | SCE_UG_Transformer2_CopperWire |  | 3P Transformer2 Copper wire assembly | UG | UG | material | Transformer
| 240 | SCE_UG_SlabBox_ConcreteBox |  | Slab box concrete box | UG | UG | material |  | Slab Box
| 241 | SCE_UG_Equipment_PME_Door1_ANIM |  | PME Exterior door 1 | UG | UG | material |  | PME |  |  |  |  | ANIMATION- want ability for door to swing outwards to 120 degrees
| 242 | SCE_UG_Equipment_PME_Door2_ANIM |  | PME Exterior door 2 | UG | UG | material |  | PME |  |  |  |  | ANIMATION- want ability for door to swing outwards to 120 degrees
| 243 | SCE_UG_Equipment_PME_Door3_ANIM |  | PME Exterior door 3 | UG | UG | material |  | PME |  |  |  |  | ANIMATION- want ability for door to swing outwards to 120 degrees
| 244 | SCE_UG_Equipment_PME_Door4_ANIM |  | PME Exterior door 4 | UG | UG | material |  | PME |  |  |  |  | ANIMATION- want ability for door to swing outwards to 120 degrees
| 245 | SCE_UG_Equipment_PME_Door1_Jbar |  | PME Door 1 Jbar | UG | UG | material |  | PME
| 246 | SCE_UG_Equipment_PME_Door3Interior_Jbar_Assembly |  | PME Door 3 Interior Jbar Assembly | UG | UG | material
| 247 | SCE_UG_Material_Elbow_600A |  | PME 600A Elbow | UG | UG | material
| 248 | SCE_UG_PME_Door1_CopperWire1 |  | PME Door 1 Copper Assembly wire 1 | UG | UG | material |  | PME
| 249 | SCE_UG_PME_Door1_CopperWire2 |  | PME Door 1 Copper Assembly wire 2 | UG | UG | material |  | PME
| 250 | SCE_UG_PME_Door1_CopperWire3 |  | PME Door 1 Copper Assembly wire 3 | UG | UG | material |  | PME
| 251 | SCE_UG_PME_Door1_CopperWireBase |  | PME Door 1 Copper Assembly wire base | UG | UG | material |  | PME
| 252 | SCE_UG_PME_Door2_CopperWire1 |  | PME Door 2 Copper Assembly wire 1 | UG | UG | material |  | PME
| 253 | SCE_UG_PME_Door2_CopperWire2 |  | PME Door 2 Copper Assembly wire 2 | UG | UG | material |  | PME
| 254 | SCE_UG_PME_Door2_CopperWire3 |  | PME Door 2 Copper Assembly wire 3 | UG | UG | material |  | PME
| 255 | SCE_UG_PME_Door3_ElbowAssembly |  | PME Door 3 Interior Elbow Assembly | UG | UG | material |  | PME
| 256 | SCE_UG_PME_Door3_Compartment |  | PME Door 3 Compartment | UG | UG | material |  | PME
| 257 | SCE_UG_Material_Elbow_200A |  | PME 200A Elbow | UG | UG | material
| 258 | SCE_UG_PME_Door3_CopperWire1 |  | PME Door 3 Copper Assembly wire 1 | UG | UG | material |  | PME
| 259 | SCE_UG_PME_Door3_CopperWire2 |  | PME Door 3 Copper Assembly wire 2 | UG | UG | material |  | PME
| 260 | SCE_UG_PME_Door3_CopperWireBase |  | PME Door 3 Copper Assembly wire base | UG | UG | material |  | PME
| 261 | SCE_UG_MiniPadTransformer_Base |  | Padmount transformer concreate base | UG | UG | material |  | Mini-Pad
| 262 | SCE_UG_MiniPadTransformer_Box |  | Padmount transformer Box | UG | UG | material |  | Mini-Pad |  |  |  | I believe this is for the small mini-pad transformer
| 263 | SCE_UG_MiniPadTransformer_BoxDoor_ANIM |  | Padmount transformer Box door | UG | UG | material |  | Mini-Pad |  |  |  |  | ANIMATION- want ability for door to swing upwards to 120 degree angle
| 264 | SCE_UG_MiniPadTransformer_ElbowAssembly |  | Padmount transformer Elbow Assembly | UG | UG | material |  | Mini-Pad
| 265 | SCE_UG_MiniPadTransformer_CopperWire1 |  | Padmount transformer Copper Assembly wire 1 | UG | UG | material |  | Mini-Pad
| 266 | SCE_UG_MiniPadTransformer_CopperWire2 |  | Padmount transformer Copper Assembly wire 2 | UG | UG | material |  | Mini-Pad
| 267 | SCE_UG_MiniPadTransformer_CopperWire3 |  | Padmount transformer Copper Assembly wire 3 | UG | UG | material |  | Mini-Pad
| 268 | SCE_UG_MiniPadTransformer_CopperWire4 |  | Padmount transformer Copper Assembly wire 4 | UG | UG | material |  | Mini-Pad
| 269 | SCE_UG_MiniPadTransformer_ConnectorWire1 |  | Padmount transformer ConnectorWire1 | UG | UG | material |  | Mini-Pad
| 270 | SCE_UG_MiniPadTransformer_ConnectorWire2 |  | Padmount transformer ConnectorWire2 | UG | UG | material |  | Mini-Pad
| 271 | SCE_UG_MiniPadTransformer_ConnectorWire3 |  | Padmount transformer ConnectorWire3 | UG | UG | material |  | Mini-Pad
| 272 | SCE_UG_MiniPadTransformer_Connector |  | Padmount transformer Connector | UG | UG | material |  | Mini-Pad
| 273 | SCE_UG_MiniPadTransformer_Connector2Cap |  | Padmount transformer Connector type 2 cap | UG | UG | material |  | Mini-Pad
| 274 | SCE_UG_MiniPadTransformer_ElbowWire1 |  | Padmount transformer Elbow wire 1 | UG | UG | material |  | Mini-Pad
| 275 | SCE_UG_MiniPadTransformer_ElbowWire2 |  | Padmount transformer Elbow wire 2 | UG | UG | material |  | Mini-Pad
| 276 | SCE_UG_MiniPadTransformer_ElbowWire3 |  | Padmount transformer Elbow wire 3 | UG | UG | material |  | Mini-Pad
| 277 | SCE_UG_MiniPadTransformer_Wire1 |  | Padmount transformer wire 1 | UG | UG | material |  | Mini-Pad
| 278 | SCE_UG_MiniPadTransformer_Wire2 |  | Padmount transformer wire 2 | UG | UG | material |  | Mini-Pad
| 279 | SCE_UG_MiniPadTransformer_Wire3 |  | Padmount transformer wire 3 | UG | UG | material |  | Mini-Pad
| 280 | SCE_UG_Equipment_Switch |  | Switch | UG | UG | equipment
| 281 | SCE_UG_Material_UtilcoBars |  | Utilco bars | UG | UG | material
| 282 | SCE_Misc_Dog |  | Dog | Wire Down | Misc
| 283 | SCE_Vehicle_Truck_F150 | Vehicle_Truck_SCE_F150 | SCE Truck | Wire Down | Vehicle | [7 empty] | ANIMATION- want ability to sit in driver side AND passenger side seats when pointed to and clicked.
| 284 | SCE_Vehicle_Truck_F150_HazardLight_ANIM | Vehicle_Truck_SCE_F150_HazardLight (SCE?) | Truck Parking light | Wire Down | Vehicle | [7 empty] | ANIMATION- want ability for parking light to be either turned off, or turned on. If on, blinking like in VR course.
| 285 | SCE_Vehicle_Truck_F150_SpotLight_ANIM | Vehicle_Truck_SCE_F150_SpotLight (SCE?) | Truck overhead spot light | Wire Down | Vehicle | [7 empty] | ANIMATION- want ability for overhead spotlight to be either turned off, or turned on. If on, shining brightly like in VR course. If possible, can spotlight rotate at its base so user can spin it around entire scene?
| 286 | SCE_Vehicle_Display_laptop |  | Digital display laptop | Wire Down | Vehicle
| 287 | SCE_OH_DownWire1 |  | Wire Down Wire 1 | Wire Down | OH | wire |  | Pole
| 288 | SCE_OH_DownWire2 |  | Wire Down Wire 2 | Wire Down | OH | wire |  | Pole
| 289 | SCE_OH_DownWire3 |  | Wire Down Wire 3 | Wire Down | OH | wire |  | Pole
| 290 | SCE_Misc_House7 |  | Stucco house | Wire Down | Misc
| 291 | SCE_Misc_Gate_Iron |  | Gate | Wire Down | Misc | [7 empty] | ANIMATION- would like ability to have left side fence gate panel open to 90 degree angle
| 292 | SCE_Misc_Fence_Iron |  | Iron fencing | Wire Down | Misc | [7 empty] | ANIMATION- would like ability to have left side fence gate panel open to 90 degree angle
| 293 | SCE_Misc_Mailbox |  | Mailbox | Wire Down | Misc
| 294 | SCE_Misc_CityBuildings |  | Scenario 2_Environment, Buildings | Wire Down | Misc
| 295 | SCE_Misc_TrafficLight |  | Traffic light | Wire Down | Misc
| 296 | SCE_Misc_RoadSign |  | Road Signage | Wire Down | Misc
| 297 | SCE_OH_DownWire4 |  | Broken wire | Wire Down | OH | wire |  | Pole
| 298 | SCE_Misc_Person1 | Add female(F), male(M), child(Ch), Adult(A) to person names, _Responder for clothing | Avatar Emergency Person | Wire Down | Misc
| 299 | SCE_Misc_Person2 |  | People Avatar 1 | Wire Down | Misc
| 300 | SCE_Misc_Person3 |  | People Avatar 2 | Wire Down | Misc
| 301 | SCE_Misc_Person4 |  | People Avatar 3 | Wire Down | Misc
| 302 | SCE_Misc_Person5 |  | People Avatar 4 | Wire Down | Misc
| 303 | SCE_Misc_Person6 |  | People Avatar 5 | Wire Down | Misc
| 304 | SCE_Misc_Person7 |  | People Avatar 6 | Wire Down | Misc
| 305 | SCE_Misc_Person8 |  | People Avatar 7 | Wire Down | Misc
| 306 | SCE_Misc_Person9 |  | People Avatar 8 | Wire Down | Misc
| 307 | SCE_Misc_Person10 |  | People Avatar 9 | Wire Down | Misc
| 308 | SCE_Tool_Flashlight |  | Emergency Torch | Wire Down | Tool | [7 empty] | ANIMATION- would like ability to be able to turn on and off torch
| 309 | SCE_Misc_DoorLock |  | Door Lock assembly | Wire Down | Misc
| 310 | SCE_Vehicle_Car1 |  | Vehicle type 1 | Wire Down | Vehicle
| 311 | SCE_Vehicle_Car2 |  | Vehicle type 2 | Wire Down | Vehicle
| 312 | SCE_Vehicle_Car3 |  | Vehicle type 3 | Wire Down | Vehicle
| 313 | SCE_Vehicle_Car4 |  | Vehicle type 4 | Wire Down | Vehicle
| 314 | SCE_Vehicle_Car5 |  | Vehicle type 5 | Wire Down | Vehicle
| 315 | SCE_Tool_CautionTape |  | Caution yellow tape | Wire Down | Tool
| 316 | SCE_Misc_Road2 |  | Road assembly for scenerio 2 | Wire Down | Misc
| 317 | SCE_Misc_Building1 |  | scenerio 2 building 1 | Wire Down | Misc
| 318 | SCE_Misc_Building2 |  | scenerio 2 building 2 | Wire Down | Misc
| 319 | SCE_Misc_Building3 |  | scenerio 2 building 3 | Wire Down | Misc
| 320 | SCE_Misc_Building4 |  | scenerio 2 building 4 | Wire Down | Misc
| 321 | SCE_Misc_Building5 |  | scenerio 2 building 5 | Wire Down | Misc
| 322 | SCE_Misc_Building6 |  | scenerio 2 building 6 | Wire Down | Misc
| 323 | SCE_Misc_Building7 |  | scenerio 2 building 7 | Wire Down | Misc
| 324 | SCE_OH_PoleAssembly |  | Scenerio Pole Assembly | Wire Down | OH
NEW CREATED ASSETS
|  | Broken pole |  |  |  | OH | material |  | pole |  |  |  | Two pieces of a pole, with cracking at top of bottom piece, and bottom of top piece
Alley-Arm
|  | Aluminum Cable Stell Reinforced (ACSR) |  |  |  | OH | wire |  | pole
|  | Aluminum Quadraplex |  |  |  | OH | wire |  | pole
|  | Aluminum Triplex |  |  |  | OH | wire |  | pole
|  | Anchor Rod and Plate |  |  |  | OH | material |  | pole
|  | Arc Flash Cat 4 Suit |  |  |  | PPE | clothing
|  | Balaclava |  |  |  | PPE | clothing
|  | Base-layer shirt |  |  |  | PPE | clothing
|  | Bracing |  |  |  | OH | material |  | pole; cross arm
|  | Brackets |  |  |  | OH | material |  | pole; cross arm
|  | Bushbar |  |  |  | Substation | equipment
|  | Capacitor |  |  |  | OH | equipment |  | pole; cross arm
|  | Circuit Breaker |  |  |  | Substation | equipment
|  | Control Room |  |  |  | Generation
|  | Copper Triplex |  |  |  | OH | wire |  | pole
|  | Copper: Bare or Weatherproof |  |  |  | OH | wire |  | pole
|  | Coverall/raingear |  |  |  | PPE | clothing
|  | Covered Conductor |  |  |  | OH | wire |  | pole
|  | Cubicle |  |  |  | Substation | equipment
|  | Engineered steel pole |  |  |  | OH | pole
|  | Expanding Rock Anchor |  |  |  | OH | material |  | pole
|  | Face shield |  |  |  | PPE | clothing
|  | FR Jacket |  |  |  | PPE | clothing | arc flash
|  | FR pants |  |  |  | PPE | clothing
|  | Generator |  |  |  | Generation
|  | Gloves |  |  |  | PPE | clothing
|  | Half Round Plastic Guy Guard |  |  |  | OH | material |  | pole
|  | Half Round Steel Guy Guard |  |  |  | OH | material |  | pole
|  | Hard hat |  |  |  | PPE | clothing
|  | High-vis vest |  |  |  | PPE | clothing
|  | Joint pole |  |  |  | OH | pole |  | pole
|  | Outer Shirt |  |  |  | PPE | clothing
|  | Pole Mounted Router |  |  |  | OH | material |  | pole
|  | post insulator |  |  |  | OH | equipment |  | pole; cross arm
|  | Power-Installed Screw Anchor (PISA) |  |  |  | OH | material |  | pole
|  | Range Finder |  |  |  | Tool
|  | Relay |  |  |  | Substation | equipment
|  | Safety glasses |  |  |  | PPE | clothing
|  | SCE Bucket Truck |  |  |  | Vehicle | truck |  |  |  | Yes | High |  | Able to stand in bucket, operate controls and move. Sit in driver seat.
|  | SCE work radio |  |  |  | Tool
|  | Sidewalk Guy |  |  |  | OH | material |  | pole
|  | silicone (pin or post type) |  |  |  |  | equipment |  | pole; cross arm
|  | suspension insulator |  |  |  | OH | equipment |  | pole; cross arm
|  | Transformer |  |  |  | Substation | equipment
|  | Transmission Line |  |  |  | OH | wire
|  | Transmission tower |  |  |  | Transmission | tower
|  | Triple-Arm |  |  |  | OH | material |  | pole
|  | Tubular PVC Guy Guard |  |  |  | OH | material |  | pole
|  | Turbine |  |  |  | Generation
|  | Weather Proof Aluminum (WAL) |  |  |  | OH | wire |  | pole
|  | Weatherhead |  |  |  | OH | material
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Naming convention- largest-->smallest hierarchy OH_pole_material_riser OH_pole_wire_triplex UG_equipment_switch
Note on N1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Describe asset, describe what you want/need it to do if required
Note on O1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does the user need to interact with this asset? How? Be specific. Does the asset need internal detail?
Note on P1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Where can image/documentation be found?