## Sheet1
Item | Scenario # | Bug/ New | Issue | Fix | Status | Submitted By & Date | Resolved By & Date | TCS Verification & Date | SCE Verfication & Date
1 |  |  | Help Senerio | Need some more time to create it | Pending
2 |  |  | Period After start | Done | Done | SCE |  | Done
3 |  |  | Remove the Numbs part of Controller | Removed the Controller parts which appear in the Left and Right hand | Done | SCE |  | Done | Done
4 |  |  | Remove 'Proceed to the main driveway gate.' |  | Done | SCE |  | Done | Done
5 |  |  | Need to remove controller part visible in hand |  | Done | SCE |  | Done | Done
6 |  |  | Period After Hazard |  | Done | SCE |  | Done | Done
7 |  |  | Great job. You identified an ESR violation. That bike was within the 3-foot by 3-foot working clearance. You advised the customer and they removed it for you | Great job. You identified a Safety hazard. That bike was within the 3-foot by 3-foot working clearance. You advised the customer and they removed it for you. | Done | SCE |  | Done | Done
8 |  |  | Great job. You identified an ESR violation. That broom was within the 3-foot by 3-foot working clearance. You advised the customer and they removed it for you | Great job. You identified a Safety hazard. That broom was within the 3-foot by 3-foot working clearance. You advised the customer and they removed it for you. | Done | SCE |  | Done | Done
9 |  |  | Great job. You identified an ESR violation. That shovel was within the 3-foot by 3-foot working clearance. You advised the customer and they removed it for you | Great job. a Safety hazard. That shovel was within the 3-foot by 3-foot working clearance. You advised the customer and they removed it for you. | Done | SCE |  | Done
10 |  |  | It is good to be aware of the wood as a potential safety hazard, but it is not within the 3 foot by 3 foot working clearance. It does not have to be removed | It is good to be aware of the wood as a potential safety hazard, but it is not within the 3 foot by 3 foot working clearance. It does not have to be removed. | Done | SCE |  | Done
11 |  |  | That is close to the 3-foot by 3-foot working clearance. You asked the customer to move them for you | It is good to be aware of the trash bin as a potential safety hazard, but it is not within the 3 foot by 3 foot working clearance. It does not have to be removed. | Done | SCE |  | Done
12 |  |  | Trash bin Need to stay after click |  | Done | SCE |  | Done
13 |  |  | Great work. You verified the wire size. Open your toolbox by pressing A button to complete Meter Spot | Great work. You verified the wire size. Open your toolbox by pressing A or B button to complete Meter Spot. | Done | SCE |  | Done
14 |  |  | Menu need to follow head | If we not pin the menu item is is always block the vision and make it uncomfortable to VR user. | Pending | SCE
15 |  |  | Phone icon need to remove |  | Done | SCE |  | Done
16 |  |  | Valid Tool list Green Tick, Invalid Tool list red tick Valid List 1,2,5,6,7 Invalid 3,4,9 | As per Comments Modified the tool selection | Done | SCE |  | Done
17 |  |  | After Gate Close popup if without closing popup if close the gate Gate Close popus stay. | If user close the Gate Gate close popup disappear | Done | SCE |  | Done
18 |  |  | Forgetting something? Remember to close the customer’s gate before leaving | Forgetting something? Remember to close the customer’s gate before leaving. | Done | SCE |  | Done
19 |  |  | Gate Need to be Closed whenever start with new Scene |  | Done | SCE |  | Done
20 |  |  | Avatar | Static Avatar added Need to add Avatar walking movement and other features | Pending | SCE
21 |  |  | Verify the all the senerios for message period. |  | Done | SCE |  | Done
22 |  |  | Without Answering question I am able to Open Gate | Fixed the issue not allowing user to open gate before answering questions | Done | SCE |  | Done
23 |  |  | Remove Log which is near air condition in scene 2 | Removed | Done | SCE |  | Done
24 |  |  | Hovering of Interested New Meter spot Postion | Activate the Correct and Incorrect new Meter Spot postion when user select the Yellow Sticker to place on new position | Done | SCE |  | Done
24 |  |  | Clear Toolpad Selection After finishing scnerio activity | Clear the Toolbox selection when user select new Scenerio | Done | SCE |  | Done
25 |  |  | Player stuck issue during playing | Fixed | Done | SCE |  | Done
26 |  |  | Grab Button Function for grabbing gate and sticker |  | Pending | SCE
27 |  |  | Tool box and Menu need to be present in front of user in any case |  | Done | SCE |  | Done
28 |  |  | Not allow player to close gate when he is inside the property |  | Done | SCE |  | Done
29 |  |  | Help Message for Overhead wire verification | We are insuring that User must verify the wire during Meter spotting, If he missed it application use to prompt before leaving the customer property. Also there is no fix oderfor user to verify overhead wire. |  | SCE
30 | ALL | NEW | Remove opening narration- "Select scene from the menu" |  | Fixed | SCE 15/6
31 | 1, 3 | NEW | eliminate ability to go around left side of house |  | Fixed | SCE 15/6
32 | 1 | NEW | Lay bike on ground in front of meter. Change Safety hazard to safety hazard in popup text. |  | Fixed | SCE 15/6
33 | 1 | NEW | Move shovel and broom to lean against meter panel. |  | Fixed | SCE 15/6
34 | 1 | NEW | Broom popup text. Change Safety hazard to safety hazard. |  | Fixed | SCE 15/6
35 | 1 | BUG | Shovel popup text error. Great job. a Safety hazard. That shovel was within the 3-foot by 3-foot working clearance. You advised the customer and they removed it for you. ADD- You identified a safety hazard. |  | Fixed | SCE 15/6
36 | 1 | BUG | Ensure blue/black bins are level on ground. |  | Fixed | SCE 15/6
37 | 1 | NEW | Move blue bin 2 feet further into backyard, away from meter. |  | Fixed | SCE 15/6
38 | 1 | NEW | Align black bin with blue bin, further into backyard. |  | Fixed | SCE 15/6
39 | 1, 2, 3 | NEW | Edit text to- ...by pressing the A or B button on your right controller to complete the meter spot. Please UPDATE on scenarios 2, 3 popup text. |  | Fixed | SCE 15/6
40 | ALL | BUG | Remove gray rectangle shading behind Tool Box square. |  | Fixed | SCE 15/6
41 | ALL | NEW | Tool Box Grid- Please make it 3x3, and then remove blank option in lower right. Please make Meter Sticker as lower right option. |  | Fixed | SCE 15/6
41.1 | 1, 2, 3 | NEW | When Rangefinder tool is selected, please have this popup text appear that has a close or X button: You won't practice this here, but the rangefinder is used to measure and record the length of overhead service wire. | New Addition | Fixed
42 | ALL | BUG | When grabbing sticker with grip button, the sticker rotates in hand, feels very unnatural. How can we grab it, and it faces forward? I have to turn my hand backwards to have sticker face me. |  | Fixed | SCE 15/6
43 | ALL | BUG | While holding sticker, I cannot move forwards using thumbstick. I move forward, it takes me backwards, quickly. I have to let go, then select it with beam, then move it back. | Need More time to fix |  | SCE 15/6
44 | ALL | BUG | Sticker able to pass through wall of house. Happens if I'm holding it, or selecting it. If I leave it behind wall, no way to get it back. Please create invisible barrier for all walls. |  | Fixed | SCE 15/6
44.1 | 1 | BUG | On text popup after placing meter sticker, change Service Connection to Service connection |  | Fixed
45 | 2 | BUG (confirmed avatar possible on May23 call) | Poor quality avatar movement. Woman is hovering/floating across deck like a ghost. Takes user out of realistic VR experience. Can her legs move? |  |  | SCE 15/6
46 | 2 | BUG (confirmed avatar possible on May23 call) | There is no avatar movement.She doesn't turn head, doesn't move arms and point to gate. Very creepy. Can you make her look in direction of where user is, like an actual person?
47 | 2 | NEW | When pointer hovers, can she be highlighted, like other objects (ie. gate)? User may not know they need to click on her.
48 | 2 | BUG | Once clicked, the popup needs to come right into field of view, not to other side. I had to turn head completely around to see popup.
49 | 2 | NEW | Change text to match this: YOU: "Hi, I'm from Edison, and I'm here to do a meter spot." Continue button. |  | Fixed
50 | 2 | NEW | Change text to: CUSTOMER: "Sounds good. It's right through the gate. And don't worry about the dog. It's very friendly." Continue button. |  | Fixed | SCE 15/6
51 |  | BUG | Now what do you do? w/ 3 options. REMOVE period after inside on second option. | Not able to find
52 | ALL | NEW | Please remove ANY periods for ANY answer choices to be consistent, in ALL scenarios. | Not able to find
53 | 2 | BUG | The dog barking noises stopped a while ago. Please have barking noises continue until user selects correct answer and clicks Continue. That would indicate the customer put dog inside. |  |  | SCE 15/6
54 | 2 | BUG | Blue bin. ADD period after removed. |  | Fixed | SCE 15/6
55 | 2 | BUG | Blue bin. Make level on ground. Looks like it is leaning. |  | Fixed
55.1 | 2 | NEW | When dog bowl is clicked on- please ADD this text to end: However, always be alert and aware even though the dog is inside. |  | Fixed
56 | 2 | BUG | Black bin- Add It does not have to be removed. |  | Fixed | SCE 15/6
57 | 2 | BUG | Black bin. Make level on ground. Looks like it is leaning. |  | Fixed
58 | 2 | New/BUG | Move wood pile into backyard, halfway between dog house and edge of house. User will need to move there and don't want them stepping on it. Text popup- Add It does not have to be removed. |  | Fixed
59 | 2 | BUG | Keep the hose in scene. Change text to: It is good to be aware of the hose as a potential safety hazard, but it is not within the 3 foot by 3 foot working clearance. It does not have to be removed. |  | Fixed | SCE 15/6
59.1 | 2 | BUG/NEW | When doghouse is clicked, it disappears. Please keep it in scene. If they click it, have text popup that says: Great job. The doghouse indicates the presence of a dog. Always be alert and aware even though the dog is inside. |  | Fixed
60 | 2 | BUG | For some reason it requires me to click OK two times for it to disappear. Please fix |  | Fixed
61 | 2/ ALL popups | BUG | When I click, the popup text is not in immediate field of view. I have to turn my head at least 90 degrees. Please have popup appear in direct field of view. Please enable this for EVERY popup so that user does NOT need to turn their heads if an object is clicked. | Snap Turn Providing |  | SCE 15/6
62 | 2 | BUG | When AC unit is clicked, all the invisible markers on wall show up. It makes it very obvious where the user is supposed to place the sticker. Can those be completely invisible to the user? | Fixed but need to verify | Fixed | SCE 15/6
63 | 2 | NEW | Remove what looks like an old window on wall. Make smooth wall because that may confuse user when trying to select best choice. | Need to check with saurab
64 | 2 | BUG | Remove red box and make invisible. Make invisible square large enough that it goes from the window to the meter panel, so that if they place the sticker in that area, they receive the feedback popup. |  | Fixed
65 | 2 | BUG | Eliminate the popup appearing when square is picked. They don't even have the meter sticker in hand. Nothing should be able to happen on wall without the meter sticker. |  | Fixed
65.1 | 2 | NEW
66 | ALL | BUG | Popup not in field of view once placed. | this would be an approved area because it has no conflicts.
67 | 1, 2, 3 | NEW | Update text for scenarios 1, 2, 3. Service connection, NOT Connection. Weatherhead, NOT weather head. |  | Fixed
68 | 2 | BUG | When holding sticker, it behaves strangely. Rotates out of control, goes behind objects. |  | Fixed
69 | 2 | NEW | When sticker placed on incorrect place (invisible square to left of meter), text popup should read: This location is not the best choice. It would require a new, longer service. Look for a better location. |  | Fixed
70 | 2 | BUG | I noticed you could place sticker on meter panel. If they do so, popup needs to say: on incorrect place (invisible square to left of meter), text popup should read: This location is not what the customer wants. Find a better location.
71 | ALL | BUG | I noticed that popups, the menu, my hands, disappear if too close to the wall and the meter panel. Can wall and meter panel be a hard barrier? | Need to Check |  | SCE 15/6
72 | 2 | NEW | Meter is from Quebec, and is Hydro. Please update front. Image reference in cell J, Row 72 | Saurab need to update |  | SCE 15/6
73 | ALL | BUG | once user leaves gate opening, they need to be able to close it. As it is now, they can't close it, and then they get popup saying Forgetting something? Close the gate. Currently they can only close it once they get that popup reminding them. Please change for ALL scenarios. | Need to modify logic and need testing |  | SCE 15/6
73.1 | ALL | BUG | There is no gate closing sound. There used to be. Can that be readded when the gate is closing, for ALL scenarios?
74 | ALL | BUG | Please have popup appear in direct field of view, wherever they are facing.
75 | 2 | BUG | Please have "What is best final step" popup appear in field of view, and follow their view. They should be facing the gate, close it, and popup appear in front of them, instead of needing to turn all the way around to notice the question popup. |  |  | SCE 15/6
76 | ALL | NEW | REMINDER to delete periods after each question choice to keep punctuation consistent. |  |  | SCE 15/6
77 | 3 | BUG | If user places sticker on meter box in blue square, a popup needs to read: Sorry, that's not a correct location for the meter. Try Again button.
77.1 | 3 | BUG? | Wherever I am located in the scenario, and I click on the meter sticker, it always appears right next to meter. Can sticker appear in my field of view? User may click sticker from toolbox anywhere so they may not know where it went.
78 |  | BUG | Meter sticker is rotating, fluttering in air when selected.
79 | 3 | BUG | Remove white square. Make square invisible and if user drops sticker in square, they receive correct feedback. Make invisible square slightly larger, expand it to the left, so they have a bigger area to place sticker.
80 | 3 | BUG | User should not be able to point at wall and see red square. Much too obvious. Make square invisible, and only time a popup appears is if the meter sticker gets placed on it.
81 | 3 | BUG | Feedback text is incorrect. Change to: This location is not a good choice. It would require a new, longer service and wire should not cross the peak of the roof. Try a better location. |  |  | SCE 15/6
82 | ALL | BUG | MAJOR ISSUE: user can simply enter gate, then leave gate and finish the scenario for ANY scenario. How can this be stopped? | Need discussion
83 | 4 | BUG | Whenver I open Scenario 4, the quality gets all pixelated. When I move my head, there are flashes of pixels. Which is why you are seeing the quality look poor on the video. Can you invesitgate why this one scenario does this? It stops once I get into the gate. | Saurab need to update
84 | 4 | BUG/NEW | Same input as scenario 2 with avatar and dog interaction. PLUS- please change avatar to an African American male, and the dog barking noise to different type of dog, preferably a smaller, friendlier sounding dog. | Saurab need to update |  | SCE 15/6
85 | 4 | NEW | We need to move things around. It's like a maze. Move bike to lean against fence right side fence. | Not understand
86 | 4 | BUG | This scenario has a different sound when selecting objects. Please keep consistent with the previous scenarios. |  | Fixed
87 | 4 | NEW | Remove log and popup from scene. |  | Fixed | SCE 15/6
88 | 4 | BUG | Move planter box to right under window. When clicked, use this popup text: It is good to be aware of the planter as a potential safety hazard, but it is not within the 3 foot by 3 foot working clearance. It does not have to be removed. |  | Fixed | SCE 15/6
89 | 4 | BUG/NEW | Move hose to under right side panel, like few inches above black part of house. Increase hose pipe to 8 inches out, extending into yard. Have hose coiled and away from meter, like towards side of house. User will need to stand there and don't want them tripping on hose. When hose is clicked, use this popup text: Great work. You identified an ESR violation. The plumbing fixture extends more than 6" from the house. You need to inform the customer the fixture must be shortened or moved. | Need model modification |  | SCE 15/6
90 | 4 | NEW | Move trash bins up against fence together, ensure they are level on ground. When each one is clicked, use this popup text: It is good to be aware of the bin as a potential safety hazard, but it is not within the 3 foot by 3 foot working clearance. It does not have to be removed. |  | Fixed
90.1 | 4 | NEW | When dog bowl is clicked on- please ADD this text to end: Always be alert and aware even though the dog is inside. |  | Fixed
91 | 4 |  | User should NOT be able to open right side panel. |  | Fixed | SCE 15/6
92 | 4 |  | Meter sticker should NOT just appear when panel is clicked. |  |  | SCE 15/6
93 | 4 |  | When left side pull section is clicked, popup text needs to appear that reads: Ensure you have your required PPE and tools by selecting the A or B button. w/ Continue button. |  |  | SCE 15/6
93.1 | 4 |  | DEV NOTE- user MUST open toolbox and select PPE/tools before being able to open panel. IF they select Faceshield, that unlocks their ability to remove cover. If Faceshield is NOT one of their selections, a popup needs to appear saying- You didn't select all the required PPE. with Try Again button.
94 | 4 |  | When meter cover is removed, and dropped, text popup appears in field of view that says: You are not allowed to break the plane of the SCE pull section for your safety. It is also best practice to knock on the box prior to opening because arachnids and insects may be nesting inside. |  |  | SCE 15/6
95 | 4 | NEW | When cable is clicked please have text popup saying- Remember to always record and take picture of the size of the underground service wire. w/Continue button. |  |  | SCE 15/6
96 | 4 | BUG | REMOVE this quiz question totally, as well as the cable image when user hovers over cables. |  |  | SCE 15/6
97 | 4 | BUG | Meter cover doesn't snap back on. It looks like it rotated? |  |  | SCE 15/6
97.1 | 4 | NEW | DEV NOTE- Is it possible to have a text popup appear if their hands reach into the meter box? Like an invisible trigger? We don't want them just reaching in and touching cables- they wouldn't in real life, but they may try in VR. If a text popup, like a warning, could come up, it would read: For your safety, you are not allowed to break the plane of the SCE pull section. The popup would appear anytime their hand went into the meter box.
98 | 4 | NEW | Replace bullet points with these: Meter Meter sticker Pull section | remove red box/meter sticker placement
99 | 5 | NEW | Delete wood log and popup from scenario. |  | Fixed | SCE 15/6
100 | 5 | NEW | Move bike to lean against right side fence |  | Fixed | SCE 15/6
101 | 5 | NEW | Move shovel and rake to lean against wall, to left side of window. Text popup is same. |  | Fixed | SCE 15/6
102 | 5 | NEW | Move black and blue trash bins to around side of house. Ensure they are level on ground. When clicked, they remain and have the text popup: It is good to be aware of the bin as a potential safety hazard, but it is not within the 3 foot by 3 foot working clearance. It does not have to be removed. |  | Fixed | SCE 15/6
103 | 5 | NEW | SAME approach/process as scenario 4. Can't open cover without going to Toolbox. THey click on cover they get prompt to open toolbox. Have to select faceshield or they can't open. Text popups, etc. |  |  | SCE 15/6
104 | 5 | BUG | Please add in the customer tampering equipment that was in storyboard. Image reference in Issue LIst doc. Not mandatory to click. If user clicks, it remains, but text popup reads: This is a type of customer measuring equipment. This is an ESR violation and needs to be removed. You would document this and inform the customer before you leave. | Saurab need to update |  | SCE 15/6 |  |  |  | Just put those two black clamps, and some white coiled cables. Not super detailed
105 | 5 | BUG | Not sure what the red box is for the meter sticker. |  |  | SCE 15/6
106 | ALL | NEW | For the Menu options. Because these apps (MEter Spotting, OH, UG, Wire Down) will all be standalone, there will be no Main Menu to go back to. Can you replace Main Menu option with- Scenario Menu and that pops up the main scenario menu in case they want to quickly start over or do another one without finishing? |  |  | SCE 15/6
107 | 1 | NEW | HELP popup text Each number should begin on it's own line. For S1- 1. Safely enter customer property. 2. Ensure safe access to meter by selecting any ESR violations or potential safety hazards. 3. Verify service wire size. 4. Open toolbox and select PPE and tools. 5. Place meter sticker on meter. 6. Safely exit customer property. |  | Fixed | SCE 15/6
108 | 2 |  | For S2- 1. Safely enter customer property. 2. Ensure safe access to meter by selecting any ESR violations or potential safety hazards. 3. Verify service wire size. 4. Open toolbox and select PPE and tools. 5. Place meter sticker on meter or different appropriate location. 6. Safely exit customer property. |  | Fixed | SCE 15/6
109 | 3 |  | For S3- 1. Safely enter customer property. 2. Ensure safe access to meter by selecting any ESR violations or potential safety hazards. 3. Verify service wire size. 4. Open toolbox and select PPE and tools. 5. Place meter sticker on meter or different appropriate location. 6. Safely exit customer property. |  | Fixed | SCE 15/6
110 | 4 |  | For S4- 1. Safely enter customer property. 2. Ensure safe access to meter by selecting any ESR violations or potential safety hazards. 3. Open toolbox and select PPE and tools. 4. Open pull section cover and verify wire size. 5. Close cover. 6. Place meter sticker on meter or different appropriate location. 7. Safely exit customer property. |  | Fixed | SCE 15/6
111 | 5 |  | For S5- 1. Safely enter customer property. 2. Ensure safe access to meter by selecting any ESR violations or potential safety hazards. 3. Open toolbox and select PPE and tools. 4. Open pull section cover and verify wire size. 5. Close cover. 6. Place meter sticker on meter or different appropriate location. 7. Safely exit customer property. |  | Fixed | SCE 15/6
112 | [5 empty] | SCE 15/6
113 | [5 empty] | SCE 15/6
114 | [5 empty] | SCE 15/6
115 | [5 empty] | SCE 15/6
116 | [5 empty] | SCE 15/6
117 | [5 empty] | SCE 15/6
118 | [5 empty] | SCE 15/6
119 | [5 empty] | SCE 15/6
120 | [5 empty] | SCE 15/6
121 | [5 empty] | SCE 15/6
122 | [5 empty] | SCE 15/6
123 | [5 empty] | SCE 15/6
124 | [5 empty] | SCE 15/6
125 | [5 empty] | SCE 15/6
126 | [5 empty] | SCE 15/6
127
128
129
130
131
131
132
133
134
135
136
137
135
136
113
114
115
116
117
118